Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 19 February 2026 |
| --- | --- |
| Team ID | LTVIP2026TMIDS46852 |
| Project Name | Importing & Securing Data in ServiceNow |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Data Import Setup | USN-1 | As an Admin, I can upload a CSV file into ServiceNow | 2 | High | Team |
| Sprint-1 | Data Import Setup | USN-2 | As an Admin, I can configure Import Set Table | 3 | High | Team |
| Sprint-1 | Data Import Setup | USN-3 | As an Admin, I can create Transform Map | 3 | High | Team |
| Sprint-1 | Employee Mapping | USN-4 | As a System, I can link Employee reference to sys_user table | 3 | High | Team |
| Sprint-1 | Security Configuration | USN-5 | As an Admin, I can create roles (Admin, HR, Manager, Employee) | 2 | High | Team |
| Sprint-2 | Security Configuration | USN-6 | As an Admin, I can configure ACL rules | 3 | High | Team |
| Sprint-2 | Reporting | USN-7 | As a Manager, I can generate department-wise report | 3 | High | Team |
| Sprint-2 | Reporting | USN-8 | As a Manager, I can generate employee-wise report | 3 | Medium | Team |
| Sprint-2 | Dashboard | USN-9 | As a Manager, I can view analytics dashboard | 5 | High | Team |
| Sprint-2 | Testing & Optimization | USN-10 | As a Team, we can perform bulk import testing | 2 | Medium | Team |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 13 | 7 Days | 01 Mar 2026 | 07 Mar 2026 | 13 | 07 Mar 2026 |
| Sprint-2 | 16 | 7 Days | 09 Mar 2026 | 15 Mar 2026 | 16 | 15 Mar 2026 |

Velocity:

Total Story Points = 13 + 16 = 29

Number of Sprints = 2

Velocity = 29 / 2

Velocity = 14.5 ≈ 15 Story Points per Sprint

Burndown Chart:

A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.

In this project:

Sprint Duration = 7 Days
Total Story Points per Sprint ≈ 15

Daily Work Completion ≈ 2–3 Story Points per Day